## Deliverables
Deliverables for Project
Deliverables
Work Package No | Deliverable Related No | Deliverable No | Deliverable Name | Description | Lead Beneficiary | Type | Dissemination Level | Due Date | New Due Date (if delay) | Delivery Date | Approval Date | Status
WP1 | D1.1 | D1 | Framework to understand barriers and benefits to apply with local legislation | Digital report containing the framework | PUCV | R | PU | 30 Apr 2025 |  | 30 Apr 2025 | 05 May 2025 | Approved
WP1 | D1.2 | D2 | A document containing the gap analysis for companies/industries | Digital report pre-identifying leverage opportunities from a macro perspective. | PUCV | R | PU | 31 Jul 2025 |  |  |  | Pending
WP1 | D1.3 | D3 | Results of the application of the innovation metrology index to target industries of the plastic value chain | Digital report containing the results with data analysis on the evaluation of each industry/company/sectors | UL | R | SEN | 31 Oct 2025 |  |  |  | Pending
WP2 | D2.1 | D4 | Repository with proposed solutions/services | This repository will consist of digital documents/pieces grouping in a visual manner the collective portfolio, the providers, and the main assets of partner institutions; to openly sharing with different targets/industries. | UA | R | PU | 30 Apr 2026 |  |  |  | Pending
WP2 | D2.2 | D5 | Document with Portfolio definition by Institution | Each University will report the portfolio designed by the institutional teams following the guidelines provided by leaders. | UNS | R | PU | 30 Apr 2026 |  |  |  | Pending
WP2 | D2.3 | D6 | Mentoring and peer-collaboration learning reports | Digital memory on the cross-matching opportunities and initiatives. | UNS | R | SEN | 30 Apr 2026 |  |  |  | Pending
WP3 | D3.1 | D7 | Comprensive problem definition on the reuse challenge | Based on provided guidelines, partners that will implement the Search Conferences methodology will conform interdisciplinary staff and researchers to prepare one-on-one conversations with defined actors (industries, social and economic actors involved in the reuse challenge, to explore in depth the leverage, and provide together a more comprehensive problems definition. All these conversations will need to be reported in a document file. | COLUMBUS | R | SEN | 31 Oct 2026 |  |  |  | Pending
WP3 | D3.2 | D8 | Report on contacts and results of interviews | The universities where the Search Conferences will be held will have identified and contacted the most relevant organisations to participate in the Search Conferences. The aim is to identify their points of interest, pre-identify concrete initiatives and engage the participation of decision-makers. | PUCV | R | PU | 31 Nov 2026 |  |  |  | Pending
WP3 | D3.3 | D9 | Benchmarking study | The identified problems involving multi-actors visions and roles are foreseen to be problems that are also faced in other countries and cities. The benchmarking will help to find inspiration in how similar multilevel problems have been approached to start identifying clues of actions. The benchmarking study will be structured as a public document available for all the partners. | PUCV - COLUMBUS | R | SEN | 2026-10-31 |  |  |  | Pending
WP3 | D3.4 | D10 | 4 Events reports (One per institution) | Each search conference will deliver a report containing the results of the 1-day event, the number of participants, the minutes of the encounter, and especially the specific solutions/projects identified among the multi-actors participants and the University. | COLUMBUS | R | SEN | 31 May 2027
WP3 | D3.5 | D11 | Updated portfolios | Universities will update the defined portfolios with the new social-multi actors initiatives that were identified and prioritized during the search conference event. The portfolio will be available in the repository. | UNS | R | PU | 31 Jun 2027 |  |  |  | Pending
WP4 | D4.1 | D12 | Report of the creative-based challenges to integrate Industry-University | This task will describe collaborative innovation challenges and their results taking into account the IP considerations of the local stakeholders. The subject will be based on the possible results of the search conferences in WP3. There will be one challenge per country integrating partnerships between industry and universities. | USACH | R | PU | 30 Apr 2027 |  |  |  | Pending
WP4 | D4.2 | D13 | Pilots definition documents | A description of each pilot at each LATAM HEI will be made. This description will contain an overview of the scope, the means of experimentation, the results and a focus will be made in the replication variants to other HEIs in Latam | UNS | R | PU | 31 Jul 2027 |  |  |  | Pending
WP4 | D4.3 | D14 | Digital Notebook with lessons and support actions | Based on the cross-evaluation, follow-up sessions report and global barriers will compended through the pilot projects. These barriers will specify the level and nature of barriers found to the collaboration Industry-University. Support actions will be documented | UC | R | PU | 31 Dec 2027 |  |  |  | Pending
WP4 | D4.4 | D15 | Document with recommendations | A global recommendation rapport will be co-created with the Latam Universities in order to map specific recommendations to each LATAM HEIs. An overall strategy for enhancing educational quality, fostering collaboration, and addressing regional challenges will be outlined, serving as a guiding framework for individual institutions to tailor their approaches and initiatives. | COLUMBUS | R | PU | 31 Jan 2028 |  |  |  | Pending
WP5 | D5.1 | D16 | Document with the dissemination digital strategy | The document with the strategy will summarize the main objectives, targets, channels, guidelines for usage, and timeline, as well all the practicalities required for a proper implementation. This strategy will be public and available for all partners digitally. | UNRN | R | SEN | 30 Apr 2025 |  | 01 May 2025 | 05 May 2025 | Approved
WP5 | D5.2 | D17 | Branding digital material and training program | The digital toolbox will contain all graphical material for branding and communication and the recommendations for usage. This will also be uploaded visible on the website. The recordings of the training - sessions will be available. | UNRN | DEC | SEN | 30 Apr 2025 |  | 09 May 2025 | 15 May 2025 | Approved
WP5 | D5.3 | D18 | Project Website and Social Media accounts | The creation of the website and social media accounts will be produced by the beginning of the project and available for all partners and targets. | UNRN | DEC | PU | 30 Jun 2025 |  |  |  | Pending
WP5 | D5.4 | D19 | Repository with materials | The repository will be hosted in the website servers to facilitate integration and wll follow the logical framework of the project and pilots to facilitate the integration and publication of materials for all partners. | UL | DEC | PU | 31 Jan 2028 |  |  |  | Pending
WP5 | D5.5 | D20 | Final conference document results | Final conference will take place by the last quarter of the project, and the results will be published on the website. | UNRN | R | PU | 31 Jan 2028 |  |  |  | Pending
WP6 | D6.1 | D21 | Quality assurance plan | UL will create a quality plan that includes the criteria and indicators to take into account in the project development. Also, it will specify the means of communication, frequency and the external advisory board that will join the project. | UL | R | SEN | 31 May 2025 |  |  |  | Pending
WP6 | D6.2 | D22 | Financial and technical management | Implementation of project management mechanisms, in their operational, financial and accountability aspects. Financial management guidelines, training, and monitoring reports will be addressed. | UL | R | SEN | 30 Jun 2025 |  |  |  | Pending
WP6 | D6.3 | D23 | Midterm Progress report | Document explaining the advancement of the project and identification of the leviers and barriers in the project development. | UL | R | SEN | 31 Jul 2026 |  |  |  | Pending